## RND Counsel_Updated Version
DEFECT TRACKING LOG FOR RND Counsel_Updated Version Application
S.No | Defect ID | Created Date | Created By | Defect Description | Module Name | Sub Module Name | User View | Assigne To | Severity | Priority | Status | Resoultion | Resolution Date | Comments
1 | RND_Councel_01 | 2018-03-01 | Kanakarajan Kandasamy | Date Filter condition is not working fine. And the Counsel Employee list should be display based on the date duration selected by the user. (Steps - > Login (PriyaTM) -> Report -> Employee -> Select From & to Date and Department -> Click Show ) | Report | Employee |  | Nivethithan Alagirisamy | Major | Medium | Closed | Done | 2017-04-01 | Issed Fiexed and working fine
2 | RND_Councel_02 | 2018-03-01 | Kanakarajan Kandasamy | There is difference between HRMS employee (584) Count and RND Counsel application Employee Count (580). (Steps - > Login (PriyaTM) ->Dashboard -> check it out counseled/uncouncseled/total sub division. | Dashboard |  |  | Nivethithan Alagirisamy | Major | Medium | Closed | Done | 2017-04-01 | Issed Fiexed and working fine
3 | RND_Councel_03 | 2018-03-01 | Kanakarajan Kandasamy | Department wise chart is not bound properly. | Dashboard |  |  | Nivethithan Alagirisamy | Major | High | Closed | Done | 2017-04-01 | Issed Fiexed and working fine
4 | RND_Councel_04 | 2018-03-01 | Kanakarajan Kandasamy | User not able to select the Solution date. (Login -> Report -> Counsel -> Drill down the Counsel code displaying in the Counsel code column (Any One) ) | Report | Counsel |  | Nivethithan Alagirisamy | Major | High | Closed | Done | 2017-04-01 | Issed Fiexed and working fine
5 | RND_Councel_05 | 2018-03-02 | Kanakarajan Kandasamy | Registred Counsel detals is not added as per the serial number order. (Login -> Register -> Register New -> Enter appropraite details -> Click Save ) | Register | Register New |  | Nivethithan Alagirisamy | Major | High | Closed | User Requirement | 2017-04-01 | Issed Fiexed and working fine
6 | RND_Councel_06 | 2018-03-01 | Kanakarajan Kandasamy | Employee Name list is not displaying for Call Center. (Login (Pradeep Kumar N ) -> Register -> Register New -> Select Department as Call Center) | Register | Register New |  | Nivethithan Alagirisamy | Major | High | Reopen | Done | 2017-04-01 | This defect still exists in the application. Please Remove it from the department dropdown list suppose if the departments not there in the ICC Process
6 | RND_Councel_07 | 2018-03-01 | Kanakarajan Kandasamy | Open status is displaying in the dropdown list for two times. (Login -> Report -> Counsel -> Drill down the Counsel code displaying in the Counsel code column (Any One) -> Select status dropdown list ) | Report | Councel |  | Nivethithan Alagirisamy | Major | High | Reopen | Done | 2017-04-01 | The defect still exists in the application and as per developer statement, this defect does not create any impact.
8 | RND_Councel_08 | 2018-03-01 | Kanakarajan Kandasamy | The status dropdown list is not displaying all the Open Status. (Login -> Report -> Counsel -> Drill down all the open status Counsel code ()displaying in the Counsel code column (Any One) | Report | Councel |  | Nivethithan Alagirisamy | Major | High | Fixed | Working Fine | 2017-04-01 | Issed Fiexed and working fine
9 | RND_Councel_09 | 2018-03-01 | Kanakarajan Kandasamy | Proper warning messag is not displaying. (Login -> Register -> Register New -> Just fill the Department,Emplayee name,Date,Issue Subject and Issue/Counsel -> Click Save ) | RE | Register New |  | Nivethithan Alagirisamy | Major | High | Fixed | Done | 2017-04-01 | Issed Fiexed and working fine
10 | RND_Councel_10 | 2018-03-01 | Kanakarajan Kandasamy | Saved Sucessfully message is displaying new page. (Login -> Report -> Counsel -> Drill down all the open status Counsel code ()displaying in the Counsel code column (Any One) -> Do modification -> Click save changes) | Report | Councel |  | Nivethithan Alagirisamy | Major | High | Fixed | Done | 2017-04-01 | Issed Fiexed and working fine
11 | RND_Councel_11 | 2018-03-01 | Kanakarajan Kandasamy | Proper warning messag is not displaying for wrong date duration selection. (Login -> Report -> Counsel -> Select Date Duration like From Date - 04/01/2018 and To date is 01/01/2018) | Report | Councel |  | Nivethithan Alagirisamy | Major | High | Fixed | Done | 2017-04-01 | Issed Fiexed and working fine