## January_ 2018_Testing Report
January Month Testing Report
Project Name | Test Date | Tested by | Assigned to | Retest Date | Comments
Walk-in for candidate | 2017-12-12 | Kanakarajan Kandasamy | Naveen Kumar | 1st Retest Date :22/12/2017. 2nd Retest Date :01/01/2018.
RND Counsel Updated Version | 2018-03-01 | Kanakarajan Kandasamy | Nivethithan Alagirisamy | 05/01//2018. | We have covered all user requiremenrts. And the applaication is in live now.
RND Dispensary | 05/01/2018 & 06/01/2018 | Kanakarajan Kandasamy | G.Arun Kumar

## HRMS_Candidate_WalkIn
DEFECT TRACKING LOG FOR WalkIn Candadite Application
S.No | Defect ID | Date created | Created By | Defect Description | Module Name | Sub Module Name | View | Assigne To | Severity | Priority | Status | Resoultion | Resolution Date | Comments
1 | WalkIn_Nov_01 | 22-12-2017 | Kanakarajan Kandasamy | SignIn and Signup Screen alignment was done properly. | Login |  | User | Naveen Kumar | Minor | Medium | Reopen
3 | WalkIn_Nov_02 | 22-12-2017 | Kanakarajan Kandasamy | Calendar is not closing after selecting the DOB | Fresher/Experience | Personal | User | Naveen Kumar | Minor | Medium | Reopen
4 | WalkIn_Nov_03 | 22-12-2017 | Kanakarajan Kandasamy | City field is allowing to enter the number | Fresher/Experience | Personal | User | Naveen Kumar | Major | Medium | Closed
4 | WalkIn_Nov_04 | 22-12-2017 | Kanakarajan Kandasamy | Save button displaying in Personal screen is not working | Fresher/Experience | Personal | User | Naveen Kumar | Critical | High | Closed
5 | WalkIn_Nov_05 | 22-12-2017 | Kanakarajan Kandasamy | Employment screen is not displaying | Experience |  | User | Naveen Kumar | Critical | High | Closed
6 | WalkIn_Nov_06 | 22-12-2017 | Kanakarajan Kandasamy | Selected Resume details are not displaying. | Fresher/Experience | Resume | User | Naveen Kumar | Major | High | Closed
7 | WalkIn_Nov_07 | 22-12-2017 | Kanakarajan Kandasamy | The screen is moving origin screen(educational) once user click on the save button | Fresher/Experience (Sign Process) |  | User | Naveen Kumar | Major | High | Reopen
8 | WalkIn_Nov_08 | 22-12-2017 | Kanakarajan Kandasamy | The screen is not stying on the same screen after completing the modification process. It's moving to the origin screen (Employment Screen) | Fresher/Experience | All Screen | User | Naveen Kumar | Major | High | Reopen
9 | WalkIn_Nov_09 | 22-12-2017 | Kanakarajan Kandasamy | Salary field is allowing to enter the alphabets. | Experience | Employement | User | Naveen Kumar | Minor | Medium | Closed
10 | WalkIn_Nov_10 | 22-12-2017 | Kanakarajan Kandasamy | Contact Person name (last company) is allowing to enter the numbers. | Experience | Employement | User | Naveen Kumar | Minor | Medium | Closed
New Bugs 01/01/2017
11 | WalkIn_Nov_11 | 2018-01-01 | Kanakarajan Kandasamy | Work To date is allowing to greater than the Current Date. | Freshers/Experience Singup and SignIn Process | Employement | User | Naveen Kumar | Major | High | New

## RND_Counsel_Updated_Version
DEFECT TRACKING LOG FOR RND Counsel_Updated Version Application
S.No | Defect ID | Created Date | Created By | Defect Description | Module Name | Sub Module Name | User View | Assigne To | Severity | Priority | Status | Resoultion | Resolution Date | Comments
1 | RND_Councel_01 | 2018-03-01 | Kanakarajan Kandasamy | Date Filter condition is not working fine. And the Counsel Employee list should be display based on the date duration selected by the user. (Steps - > Login (PriyaTM) -> Report -> Employee -> Select From & to Date and Department -> Click Show ) | Report | Employee |  | Nivethithan Alagirisamy | Major | Medium | Closed | Done | 2017-04-01 | Issed Fiexed and working fine
2 | RND_Councel_02 | 2018-03-01 | Kanakarajan Kandasamy | There is difference between HRMS employee (584) Count and RND Counsel application Employee Count (580). (Steps - > Login (PriyaTM) ->Dashboard -> check it out counseled/uncouncseled/total sub division. | Dashboard |  |  | Nivethithan Alagirisamy | Major | Medium | Closed | Done | 2017-04-01 | Issed Fiexed and working fine
3 | RND_Councel_03 | 2018-03-01 | Kanakarajan Kandasamy | Department wise chart is not bound properly. | Dashboard |  |  | Nivethithan Alagirisamy | Major | High | Closed | Done | 2017-04-01 | Issed Fiexed and working fine
4 | RND_Councel_04 | 2018-03-01 | Kanakarajan Kandasamy | User not able to select the Solution date. (Login -> Report -> Counsel -> Drill down the Counsel code displaying in the Counsel code column (Any One) ) | Report | Counsel |  | Nivethithan Alagirisamy | Major | High | Closed | Done | 2017-04-01 | Issed Fiexed and working fine
5 | RND_Councel_05 | 2018-03-02 | Kanakarajan Kandasamy | Registred Counsel detals is not added as per the serial number order. (Login -> Register -> Register New -> Enter appropraite details -> Click Save ) | Register | Register New |  | Nivethithan Alagirisamy | Major | High | Closed | User Requirement | 2017-04-01 | Issed Fiexed and working fine
6 | RND_Councel_06 | 2018-03-01 | Kanakarajan Kandasamy | Employee Name list is not displaying for Call Center. (Login (Pradeep Kumar N ) -> Register -> Register New -> Select Department as Call Center) | Register | Register New |  | Nivethithan Alagirisamy | Major | High | Reopen | Done | 2017-04-01 | This defect still exists in the application. Please Remove it from the department dropdown list suppose if the departments not there in the ICC Process
6 | RND_Councel_07 | 2018-03-01 | Kanakarajan Kandasamy | Open status is displaying in the dropdown list for two times. (Login -> Report -> Counsel -> Drill down the Counsel code displaying in the Counsel code column (Any One) -> Select status dropdown list ) | Report | Councel |  | Nivethithan Alagirisamy | Major | High | Reopen | Done | 2017-04-01 | The defect still exists in the application and as per developer statement, this defect does not create any impact.
8 | RND_Councel_08 | 2018-03-01 | Kanakarajan Kandasamy | The status dropdown list is not displaying all the Open Status. (Login -> Report -> Counsel -> Drill down all the open status Counsel code ()displaying in the Counsel code column (Any One) | Report | Councel |  | Nivethithan Alagirisamy | Major | High | Fixed | Working Fine | 2017-04-01 | Issed Fiexed and working fine
9 | RND_Councel_09 | 2018-03-01 | Kanakarajan Kandasamy | Proper warning messag is not displaying. (Login -> Register -> Register New -> Just fill the Department,Emplayee name,Date,Issue Subject and Issue/Counsel -> Click Save ) | RE | Register New |  | Nivethithan Alagirisamy | Major | High | Fixed | Done | 2017-04-01 | Issed Fiexed and working fine
10 | RND_Councel_10 | 2018-03-01 | Kanakarajan Kandasamy | Saved Sucessfully message is displaying new page. (Login -> Report -> Counsel -> Drill down all the open status Counsel code ()displaying in the Counsel code column (Any One) -> Do modification -> Click save changes) | Report | Councel |  | Nivethithan Alagirisamy | Major | High | Fixed | Done | 2017-04-01 | Issed Fiexed and working fine
11 | RND_Councel_11 | 2018-03-01 | Kanakarajan Kandasamy | Proper warning messag is not displaying for wrong date duration selection. (Login -> Report -> Counsel -> Select Date Duration like From Date - 04/01/2018 and To date is 01/01/2018) | Report | Councel |  | Nivethithan Alagirisamy | Major | High | Fixed | Done | 2017-04-01 | Issed Fiexed and working fine