## RND Counsel_Updated Version
DEFECT TRACKING LOG FOR RND Dispensary Application
S.No | Defect ID | Created Date | Created By | Defect Description | Module Name | Sub Module Name | User View | Assigne To | Severity | Priority | Status | Resoultion | Resolution Date | Tester Comments
1 | RND_Disp_01 | 2018-05-01 | Kanakarajan Kandasamy | SignUp link displaying along with "Don't have an account? ". | Login |  | Doctors | G Arun Kumar | Major | Medium | Closed | Removed | 2018-06-01 | Defect Fixed
2 | RND_Disp_02 | 2018-05-01 | Kanakarajan Kandasamy | A proper warning message is not displaying for the invalid UserName and Password Entry. | Login |  | Doctors | G Arun Kumar | Minor | Medium | Closed | This is not a issue | 2018-06-01 | NA
3 | RND_Disp_03 | 2018-05-01 | Kanakarajan Kandasamy | Proper Logged In User Name is not displaying In the RND Dispensary Application. (Steps:- Login -> Check it the logged in username displaying on the top right corner of the page.) | RND Dispensary |  | Doctors | G Arun Kumar | Major | High | Closed | kindly check the DB for verify real name and username as per functionality this is works fine | 2018-06-01 | NA
4 | RND_Disp_04 | 2018-05-01 | Kanakarajan Kandasamy | Getting confuse the names (Doctor and Doctor1) displaying above to the Navigation bar. And Remove Navigation Label. (Steps:- Login -> Check it the names are displaying above the navigation bar.) | RND Dispensary |  | Doctors | G Arun Kumar | Major | High | Reopen | kindly check the DB for verify real name and username as per functionality this is works fine, Not valid. This case like name shake | 2018-06-01 | I have not created this bug for name shake bug. With respect to Quality Defect is a defect. A defect may be Showstopper, Critical, major, minor or cosmetic defect.
5 | RND_Disp_05 | 2018-05-01 | Kanakarajan Kandasamy | Proper placeholder like "Seach for the employee " not displaying in the Search textBox.(Steps:- Login -> Consulting -> Check it out in Seach test box.) | Consulting | Search Employee | Doctors | G Arun Kumar | Minor | High | Closed | NA | 2018-06-01 | Defect Fixed
6 | RND_Disp_06 | 2018-05-01 | Kanakarajan Kandasamy | Screen Name is Not displaying for the Employee Visit Entry Form page | Consulting | Search Employee | Doctors | G Arun Kumar | Major | High | Closed | NA | 2018-06-01 | Defect Fixed
7 | RND_Disp_07 | 2018-05-06 | Kanakarajan Kandasamy | The proper placeholder is not displaying.(Steps:- Login -> Consulting -> Enter Employee name / Employee ID -> Click on the Employee name displaying in the Employee details grid -> Check it out the Height and Weight Field.) | Consulting | Search Employee | Doctors | G Arun Kumar | Major | High | Reopen | Refered from form-get website | 2018-06-01 | Not Yet fixed this issue
8 | RND_Disp_08 | 2018-06-01 | Kanakarajan Kandasamy | How long have you had this pain/problem? Filed should be like a text box and it should allow entering the alphanumerical character. .(Steps:- Login -> Consulting -> Enter Employee name / Employee ID -> Click on the Employee name displaying in the Employee details grid -> Check it out the How long have you had this pain/problem? Field.) | Consulting | Search Employee | Doctors | G Arun Kumar | Major | High | Closed | Refered from form-get website and confirmed with rajesh | 2018-06-01 | NA
9 | RND_Disp_09 | 2018-06-01 | Kanakarajan Kandasamy | Difficult to identify the mandatory fields in the form. .(Steps:- Login -> Consulting -> Enter Employee name / Employee ID -> Click on the Employee name displaying in the Employee details grid -> Employee Vist entry form ) | Consulting | Search Employee | Doctors | G Arun Kumar | Major | High | Closed | NA | 2018-06-01 | Defect Fixed
10 | RND_Disp_10 | 2018-06-01 | Kanakarajan Kandasamy | Diagnosis, Mention Details, Associated signs/Symptoms fields are allowing to enter the more than 500 characters but after click on the Submit Button User getting " Enter Less than 500 characters " warning popup box is populating.(Steps :- Login -> Consulting -> Enter Employee name / Employee ID -> Click on the Employee name displaying in the Employee details grid -> Employee Vist entry form -> fill all the details (Enter more than 500 character in Diagnosis, Mention Details,Associated signs/Symptoms fields )) -> Click Submit) | Consulting | Search Employee | Doctors | G Arun Kumar | Major | High | Reopen | NA | 2018-06-01 | Still are getting the same problem for Diagnosis field
11 | RND_Disp_11 | 2018-06-01 | Kanakarajan Kandasamy | Doctor feedback field is allowing to enter the more than 100 characters but after click on the Submit Button User getting " Enter Less than 100 characters " warning popup box is populating ..(Steps:- Login -> Consulting -> Enter Employee name / Employee ID -> Click on the Employee name displaying in the Employee details grid -> Employee Vist entry form -> fill all the details (Enter more than 100 characters in Doctor feedback field )) -> Click Submit) | Consulting | Search Employee | Doctors | G Arun Kumar | Major | High | Reopen | NA | 2018-06-01 | Not Yet fixed this issue
12 | RND_Disp_12 | 2018-06-01 | Kanakarajan Kandasamy | Proper message is not displaying After submitting the Employee Consulting History.(Steps :- Login -> Consulting -> Enter Employee name / Employee ID -> Click on the Employee name displaying in the Employee details grid -> Employee Vist entry form -> fill all the mandatory details -> Click Submit) | Consulting | Search Employee |  | G Arun Kumar | Major | High | Reopen | It works fine and it shows message "Patient visit entry saved successfully!!" after submiting patient visit entry form | 2018-06-01 | "Patient visit entry saved successfully!!" message should be displayed navigation before the Patient Vist History page. If the client accepts the comments that resolution column. Another wise I will this will be in Reopen status.
13 | RND_Disp_13 | 2018-06-01 | Kanakarajan Kandasamy | Not able to view the respective Employee Medical History anywhere in the application. Particularly in History of Patient Visits. | Consulting | Search Employee | Doctors | G Arun Kumar | Major | High | Reopen | Kindly understand web application nature and it functionality. Also mention bug as bug and feature as new feature don’t try confuse developers | 2018-06-01 | I have understood the application flow. Why have not added Edit button on the Patient Vist History page? before sending the application for testing. Doctor user has to show the patient medical history in Patient Vist History.
14 | RND_Disp_14 | 2018-06-01 | Kanakarajan Kandasamy | Edit Name Button is not so meaningful (Discuss with the client and add proper name) because Doctors is not going edit the details, He is going to add the details selecting details displaying on the Medical History model popup.(Steps :- Login -> Consulting -> Enter Employee name / Employee ID -> Click on the Employee name displaying in the Employee details grid -> Employee Vist entry screen -> Edit Button ) | Consulting | Search Employee | Doctors | G Arun Kumar | Major | High | Reopen | The Name "Edit" is enough. If patient visit at second time what would be the button name, just thing and make entry in test report. | 2018-06-01 | Edit Button is there in the application for updating the Patient Vist History. So think about first time entry.
15 | RND_Disp_15 | 2018-06-01 | Kanakarajan Kandasamy | Both X symbol and close functionality are same so remove X symbol displaying in the Employee Medical History Model popup. (Steps :- Login -> Consulting -> Enter Employee name / Employee ID -> Click on the Employee name displaying in the Employee details grid -> Employee Vist entry screen -> Click Edit Button -> Employee Medical History ) | Consulting | Search Employee | Doctors | G Arun Kumar | Major | High | Reopen | Don’t enter test case as name shake | 2018-06-01 | I have not created this bug for name shake bug. With respect to Quality Defect is a defect. A defect may be Showstopper, Critical, major, minor or cosmetic defect. Same functionality should not be repeated. I request you refer the comments what have mentioned in the resolution column for Test case ID RND_Disp_21.
16 | RND_Disp_16 | 2018-06-01 | Kanakarajan Kandasamy | " Patient visit entry saved successfully!! " message should not displayed here. (Steps :- Login -> Consulting -> Enter Employee name / Employee ID -> Click on the Employee name displaying in the Employee details grid -> Employee Vist entry form -> fill all the mandatory details -> Click Submit -> Patient visit history) | Consulting | Patient History History | Doctors | G Arun Kumar | Major | High | Reopen | Understand the web application nature | 2018-06-01 | I have understood the application flow. "Patient visit entry saved successfully!!" message should not be displayed here. I will close it immediately If end user accepts.Otherwise, this defect will be in Reopen Status.
17 | RND_Disp_17 | 2018-06-01 | Kanakarajan Kandasamy | Employee Vist entry screen form should be displayed as a blank its allow to insert the repeated entry for the same patient. (Steps :- Login -> Consulting -> Enter Employee name / Employee ID -> Click on the Employee name displaying in the Employee details grid -> Employee Vist entry form -> fill all the mandatory details -> Click Submit -> Click on the <- (Previous) symbol displaying on the URL Bar. | Consulting | Search Employee | Doctors | G Arun Kumar | Major | High | Reopen | Not valid bug report | 2018-06-01 | Don't say this one is not a valid bug. I request you Refer the steps that I have mentioned in the Defect description column.
18 | RND_Disp_18 | 2018-06-02 | Kanakarajan Kandasamy | Patient History page Is not aligned properly. (Steps :- Login -> Consulting ->Patient Visit History ) | Consulting | Patient Visit History | Doctors | G Arun Kumar | Major | High | Reopen | It aligned as much as possible | 2018-06-01 | Still, alignement problem is exiting in the page
19 | RND_Disp_19 | 2018-06-01 | Kanakarajan Kandasamy | We entered 5.6 as the patient height in the employee height field of the Employee Vist Entry form. But In-Patient History the Height is displaying as a 5.60. (Steps :- Login -> Consulting -> Enter Employee name / Employee ID -> Click on the Employee name displaying in the Employee details grid -> Employee Vist entry screen -> fill all the mandatory details -> Click Submit -> Patient History -> Check it out in Height Colum) | Consulting | Patient Visit History | Doctors | G Arun Kumar | Major | High | Closed | NA |  | Defect Fixed
20 | RND_Disp_20 | 2018-06-01 | Kanakarajan Kandasamy | We entered 20 as the patient weight in the employee weight field of the Employee Vist Entry form. But In-Patient History the Height is displaying as a 20.00 (Steps:- Login -> Consulting -> Enter Employee name / Employee ID -> Click on the Employee name displaying in the Employee details grid -> Employee Vist entry screen -> fill all the mandatory details -> Click Submit -> Patient History -> Check it out in Weight Colum) | Consulting | Patient Visit History | Doctors | G Arun Kumar | Major | High | Closed | NA |  | Defect Fixed
21 | RND_Disp_21 | 2018-06-01 | Kanakarajan Kandasamy | Getting confuse the names (Doctor and Doctor1) displaying above to the Navigation bar. And Remove Navigation Label. (Steps:- Login -> Consulting -> Patient Visit History -> Check it the names are displaying above the navigation bar ) | Consulting | Patient Visit History | Doctors | G Arun Kumar | Major | High | Reopen | Repeated test case | 2018-06-01 | Yes, this defect is a repeated defect I agree with you..but still, this defect exists on the page.
22 | RND_Disp_22 | 2018-06-01 | Kanakarajan Kandasamy | Proper message is not displaying after deleting the Patient Visit History. (Steps:- Login -> Consulting -> Patient Visit History -> Click on the Delete button displaying on the Patient visit History record) | Consulting | Patient Visit History | Doctors | G Arun Kumar | Major | High | Closed | It works fines, after deleting the record it will shows the message like "Patient visit entry deleted successfully!!" |  | NA
23 | RND_Disp_23 | 2018-06-01 | Kanakarajan Kandasamy | The Page is navigating to the " Employee Vist entry Page ". (Steps :- Login -> Consulting -> Patient Visit History -> Click On the <- (Previous) symbol displaying in the URL Bar.) | Consulting | Patient Visit History | Doctors | G Arun Kumar | Major | High | Not a Bug | Works fine | 2018-06-01 | NA
24 | RND_Disp_24 | 2018-06-01 | Kanakarajan Kandasamy | Reset button functionality is not working fine. (Steps:- Login -> Consulting -> Patient Visit History -> Click on the Edit button displaying on the Patient visit History record -> Click Reset button displaying in the Edit Counseling employee Form) | Consulting | Patient Visit History | Doctors | G Arun Kumar | Major | High | Reopen | Please read this test case twice or thrice, Tester entered as the reset button working as fine then what is the purpose make this bug report | 2018-06-01 | I have not added "Not " in the sentence.I have corrected the mistakes. Now check it out and fix the defect.
25 | RND_Disp_25 | 2018-06-01 | Kanakarajan Kandasamy | Patietn Visit History report is not bound properly in PDF file.(Steps:- Login -> Consulting -> Patient Visit History -> Click on the PDF button) | Consulting | Patient Visit History | Doctors | G Arun Kumar | Major | High | Reopen | This is not a issue, We focussed on only excel report | 2018-06-01 | Then what is the purpose of generating the PDF report
26 | RND_Disp_26 | 2018-06-01 | Kanakarajan Kandasamy | Action column is not necessary to dispaying in Report. (Steps:- Login -> Consulting -> Patient Visit History -> Click on the Copy/Excel/PDF button -> Check it out in report) | Consulting | Patient Visit History | Doctors | G Arun Kumar | Major | High | Reopen | This is not a issue | 2018-06-01 | This is an Issue
27 | RND_Disp_25 | 2018-06-01 | Kanakarajan Kandasamy | Add Consult date (extra functionality) in the Employee Vist entry form (Steps:- Login -> Consulting -> Enter Employee name / Employee ID -> Click on the Employee name displaying in the Employee details grid -> Employee Vist entry form | Consulting | Search Employee | Doctors | G Arun Kumar | New Functionality |  | Reopen | Invalid feature do cant implement. | 2018-06-01 | Regarding this Functionality, I had discussed with Mr.Rajesh. After Getting his confirmation only I have added this functionality. So you have to implement